## Sheet1
Predecessor_id | Successor_id | Relationship_typ | Predecessor_activ_status | successor_activ_tatus | lag(d) | Predecessor_activ_name | Successor_activ_name
Z2.01A.GF.EL | Z2.01A.GF.3 | FS | Completed | Not Started | 0 | Install Empty Embedded Conduits - [Ground Floor] [01A] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls- [Wet Areas] - [Ground Floor] [01A] - [Group 02] - [Zone 02]
Z2.01A.1F.EL | Z2.01A.1F.3 | FS | Completed | Not Started | 0 | Install Empty Embedded Conduits - [First Floor] [01A] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls- [Wet Areas] - [First Floor] [01A] - [Group 02] - [Zone 02]
Z2.01A.RF.EL | Z2.01A.RF.3 | FS | Completed | Not Started | 0 | Install Empty Embedded Conduits - [Roof Floor] [01A] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls- [Wet Areas] - [Roof Floor] [01A] - [Group 02] - [Zone 02]
Z2.01B.GF.EL | Z2.01B.GF.3 | FS | In Progress | Not Started | 0 | Install Empty Embedded Conduits - [Ground Floor] [01B] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls- [Wet Areas] - [Ground Floor] [01B] - [Group 02] - [Zone 02]
Z2.01B.1F.EL | Z2.01B.1F.3 | FS | In Progress | Not Started | 0 | Install Empty Embedded Conduits - [First Floor] [01B] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls- [Wet Areas] - [First Floor] [01B] - [Group 02] - [Zone 02]
Z2.01B.RF.EL | Z2.01B.RF.3 | FS | In Progress | Not Started | 0 | Install Empty Embedded Conduits - [Roof Floor] [01B] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls- [Wet Areas] - [Roof Floor] [01B] - [Group 02] - [Zone 02]
Z2.01A.GF.HV | Z2.01A.GF.1 | SS | Not Started | Not Started | 0 | Install UPVC Conduits for High Wall Split Units Refrigerant Pipes - [Ground Floor] [01A] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls and Cieling -[Ground Floor] [01A] - [Group 02] - [Zone 02]
Z2.01A.1F.HV | Z2.01A.1F.1 | SS | Not Started | Not Started | 0 | Install UPVC Conduits for High Wall Split Units Refrigerant Pipes - [First Floor] [01A] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls and Cieling -[First Floor] [01A] - [Group 02] - [Zone 02]
Z2.01A.RF.HV | Z2.01A.RF.1 | SS | Not Started | Not Started | 0 | Install UPVC Conduits for High Wall Split Units Refrigerant Pipes - [Roof Floor] [01A] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls and Cieling - [Roof Floor] [01A] - [Group 02] - [Zone 02]
Z2.01B.GF.HV | Z2.01B.GF.1 | SS | Not Started | Not Started | 0 | Install UPVC Conduits for High Wall Split Units Refrigerant Pipes - [Ground Floor] [01B] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls and Cieling -[Ground Floor] [01B] - [Group 02] - [Zone 02]
Z2.01B.1F.HV | Z2.01B.1F.1 | SS | Not Started | Not Started | 0 | Install UPVC Conduits for High Wall Split Units Refrigerant Pipes - [First Floor] [01B] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls and Cieling -[First Floor] [01B] - [Group 02] - [Zone 02]
Z2.01B.RF.HV | Z2.01B.RF.1 | SS | Not Started | Not Started | 0 | Install UPVC Conduits for High Wall Split Units Refrigerant Pipes - [Roof Floor] [01B] - [Group 02] - [Zone 02] | Apply Internal Cement Plaster for Walls and Cieling - [Roof Floor] [01B] - [Group 02] - [Zone 02]